## KITFOX TIME
KitFox Classic Mark IV Time Sheet
| TOTAL HOURS TO DATE |  |  |  |  | KitFox Classic Mark IV Time Sheet |  | Based on 1200 Hours |  | Based on 1500 Hours |  | Based on 2000 Hours |  |  | Total Dollars Invested
| 79.5 |  |  |  |  | FINISH DATE |  | 2027-05-22 02:53 |  | 2027-08-09 08:46 |  | 2027-12-19 10:35 |  |  | 362.33
[6 empty] | % COMPLETE |  | 6.625% |  | 5.3% |  | 3.975%
[6 empty] | MONTH RATE |  | 115.1488 |  | 115.1488 |  | 115.1488
|  |  | 14 mos. 1350 hrs |  |  | TOTAL MONTHS |  | 0.69041 |  | 0.69041 |  | 0.69041
1900-01-20 | DATE |  | HOURS |  | WRKR | ACTIVITY | MANUAL SECTION |  | PHOTO LOG # |  | WEEK ENDING |  | ACTUAL HOURS |  | WEEKLY TARGET |  | GRAND AVERAGE
1 | 2006-09-17 |  | 8 |  | Bob | Wing Sub-section A - Built wing jig, spar inserts - Steps 1-8 | Wing-A |  | 9_16_2006 |  | 2006-09-17 |  | 8 |  | 15 |  | 26.5
1 | 2006-09-23 |  | 4 |  | Bob | Wing Sub-section A - Spar prep - remove scratches | Wing-A |  |  |  | 2006-09-24 |  | 12 |  | 15 |  | 26.5
1 | 2006-09-24 |  | 2.5 |  | Bob | Wing Sub-section A - Steps 7-11. | Wing-A |  | 9_24_2006 |  | 2006-09-24 |  | 14.5 |  | 15 |  | 26.5
1 | 2006-09-30 |  | 4 |  | Bob | Wing Sub-section A - Step 12 (right wing) | Wing-A |  |  |  | 2006-10-01 |  | 18.5 |  | 15 |  | 26.5
1 | 2006-10-02 |  | 4 |  | Bob | Wing Sub-section A - Steps 7-12 (left wing) | Wing-A |  | 10_2_2006 |  | 2006-10-08 |  | 22.5 |  | 15 |  | 26.5
1 | 2006-10-21 |  | 2 |  | Bob | Wing Sub-section A - Steps 13-14 (both wings) | Wing-A |  | 10_21_2006 |  | 2006-10-22 |  | 24.5 |  | 15
1 | 2006-11-18 | 1 | 2 |  | Bob | Wing Sub-section A - Steps 15-16 (right wing) | Wing-A |  |  | 1 | 2006-11-19 | 1 | 26.5 | 1 | 15 | #REF! | 26.5
1 | 2006-11-19 | 1 | 3 |  | Bob | Wing Sub-section A - Steps 17-20 (right wing) | Wing-A |  |  | 1 | 2006-11-19 | 1 | 29.5 | 1 | 15 |  | 26.5
1 | 2006-12-22 | 1 | 3.5 |  | Bob | Wing Sub-section A - Steps 15-19 (left wing) | Wing-A |  | 12_22_2006 | 1 | 2006-12-24 | 1 | 33 | 1 | 15 | #REF!
1 | 2006-12-23 | 1 | 3.5 |  | Bob | Wing Sub-section A - Steps 20 (left wing) - 21 both, partially | Wing-A |  | 12_23_2006 | 1 | 2006-12-24 | 1 | 36.5 | 1 | 15 | #REF! | 26.5
1 | 2006-12-25 | 1 | 1 |  | Bob | Wing Sub-section A - Step 21 (both wings) | Wing-A |  |  | 1 | 2006-12-31 | 1 | 37.5 | 1 | 15 | #REF!
1 | 2006-12-26 | 1 | 6 | #REF! | Bob | Wing Sub-section A - Step 22 (partial), 23, and 31 (pattern) (both wings) | Wing-A |  | 12_26_2006 | 1 | 2006-12-31 | 1 | 43.5 | 1 | 15 | #REF!
1 | 2006-12-29 | 1 | 2 |  | Bob | Wing Sub-section A - Step 22 (both wings) | Wing-A |  | 12_29_2006 |  | 2006-12-31 | 1 | 45.5 |  | 15 |  | 26.5
1 | 2006-12-31 | 1 | 4 |  | Bob | Wing Sub-section A - Corrosion Protection - sloshed spars and braces with metal prep, primed brackets | Wing-A |  | 12_31_2006 |  | 2006-12-31 | 1 | 49.5 |  | 15
1 | 2007-01-01 | 1 | 4 |  | Bob | Wing Sub-section A - Corrosion Protection - sloshed spars and braces with Alodine 1201 | Wing-A |  | 1_01_2007 |  | 2007-01-07 |  | 53.5 |  | 15
1 | 2007-01-06 | 1 | 4 |  | Bob | Wing Sub-section A - Step 32 (rear spar attach reinforcements) | Wing-A |  | 1_06_2007 |  | 2007-01-07 |  | 57.5
1 | 2007-01-08 | 1 | 2 |  | Bob | Wing Sub-section A - Step 32 (front spar attach reinforcements) | Wing-A |  |  |  | 2007-01-14 |  | 59.5
1 | 2007-01-13 | 1 | 2 |  | Bob | Wing Sub-section A - Step 32 (front spar attach reinforcements) | Wing-A |  | 1_13_2007 |  | 2007-01-14 |  | 61.5
1 | 2007-03-24 | 1 | 2 |  | Bob | Fuel Tanks - pressure and leak test, clean with water. | Wing-A |  |  |  | 2007-03-25 |  | 63.5
1 | 2007-04-21 | 1 | 8 |  | Bob | Wing Sub-section A - Steps 24-29 (right wing build) | Wing-A |  | 4_21_2007 |  | 2007-04-22 |  | 71.5
1 | 2007-05-19 | 1 | 8 |  | Bob | Wing Sub-section A - Steps 24-30 (left wing build) | Wing-A |  | 5_19_2007 |  | 2007-05-20 |  | 79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5
79.5

## INVESTMENT
INVESTMENT |  | 362.33 | TOTALS
DATE | PRODUCT | PAYEE | AIRFRAME | ENGINE | PROP | ELECTRICAL | TOOLS | AVIONICS | INFO | FREIGHT | SUPPLIES | ENG INST LABOR | PAINT | INTERIOR
| TOTALS: | [5 empty] | 340.52 |  |  | 21.81
2006-09-17 | Tool Acquisition (Sept.) | Aircraft Spruce & Home Depot |  |  |  |  | 320.87 |  |  | 15.13
2006-11-20 | Tool Acquisition (Nov.) | Aircraft Spruce |  |  |  |  | 19.65 |  |  | 6.68